BLAU BATCH

Official Distributor for Coraplast Masterbatch

MARKETING CAMPAIGN PLAN

Black & White Masterbatch Product Launch

Prepared by Blau Batch Marketing

March 2026

Version 1.0

# 1. Campaign Overview

## Campaign Name

"Powered by Coraplast" — The Color Masterbatch Launch by Blau Batch

## Campaign Summary

Blau Batch has become an authorized distributor for Coraplast, a leading masterbatch manufacturer. This campaign introduces Coraplast's Black and White Masterbatch portfolio — and custom color grades upon request — to plastic manufacturers, packaging companies, and construction-sector clients across Egypt.

## Primary Objective

Generate 60+ qualified leads and convert 15+ new product trials within 8 weeks of campaign launch (April – May 2026).

## Secondary Objectives

- Inform all existing Blau Batch clients of the Coraplast partnership within the first 2 weeks

- Position Blau Batch as a full-service masterbatch supplier (Filler + Color)

- Establish Coraplast brand recognition in the Egyptian plastics market

- Build a qualified prospect pipeline for colored masterbatch on request

# 2. Target Audience

| Segment | Profile | Pain Points | Buying Stage |
| --- | --- | --- | --- |
| Plastic Manufacturers | Injection molding, extrusion, and blow molding facilities | Inconsistent color quality, limited local supplier options | Consideration |
| Packaging Companies | Food, pharma & consumer goods packaging producers | Need FDA/EU food-grade compliance, opacity control | Consideration / Decision |
| Construction Sector | Pipes, profiles, geomembranes, and building materials producers | UV stability, durability, heat resistance requirements | Awareness / Consideration |
| Existing Blau Batch Clients | Current Filler Masterbatch buyers | Sourcing color masterbatch from multiple suppliers | Decision (warm audience) |

## Highest Priority Segment

Existing Blau Batch clients are the warmest audience — they already trust the brand and relationship. Prioritize direct outreach to this group in Week 1.

# 3. Key Messages

## Core Message

Blau Batch is now your single source for high-performance Filler Masterbatch AND premium Black, White, and Custom Color Masterbatch — powered by Coraplast.

## Supporting Messages

For All Audiences — Partnership Announcement

- Blau Batch is now an official Coraplast distributor, bringing internationally proven masterbatch grades to Egypt.

- Coraplast's products comply with RoHS directive and EU food safety standards (AP 89/1) — quality that meets global specifications.

For Packaging Companies

- Food-grade White Masterbatch grades (EU AP 89/1 and US FDA compliant) for clean, safe packaging.

- High TiO2 concentration grades (up to 75%) for maximum opacity and whiteness in flexible and rigid packaging.

For Plastic Manufacturers

- 40+ Black Masterbatch grades (PE and PP based) — from 20% HAF filler grades to 45% carbon black grades for any application.

- Excellent dispersion, heat stability up to 280°C, and non-toxic formulations.

For Construction Sector

- UV-stabilized masterbatch grades and specialty processing aids for longer-lasting plastic products.

- Black grades with proven weatherability — ideal for pipes, conduit, and outdoor profiles.

For Existing Blau Batch Clients

- As an existing Blau Batch client, you get first access to the Coraplast range — fewer suppliers, simpler procurement.

- One trusted partner for all your masterbatch needs: Filler, Black, White, and Color.

# 4. Channel Strategy

| Channel | Why It Fits | Content Format | Effort | Priority |
| --- | --- | --- | --- | --- |
| Direct Client Outreach (Phone / WhatsApp) | Fastest path to existing client base — warm leads already trust Blau Batch | Personalized message + product catalog PDF | Low | HIGHEST |
| Email Campaign | Cost-effective, professional, trackable — reaches procurement & technical staff | HTML email announcement + product spec sheets | Low-Medium | High |
| LinkedIn (Organic) | B2B decision makers in manufacturing and procurement actively use LinkedIn in Egypt | Partnership announcement post, product highlight posts, technical tips | Medium | High |
| Product Catalog / Data Sheets | Technical buyers need spec sheets to evaluate and approve new materials | Branded PDF catalog of Coraplast Black & White grades distributed by Blau Batch | Medium | High |
| WhatsApp Broadcast | High open rates in Egypt — ideal for quick announcements and follow-up | Short announcement message + PDF attachment | Low | Medium |
| Website Update (blaubatch.com) | Validates the partnership for prospects doing research; supports SEO | New product page for Coraplast range + partnership banner | Medium | Medium |

# 5. Content Calendar (8 Weeks)

Campaign Window: April 1 – May 31, 2026

| Week | Content Piece | Channel | Notes / Dependencies | Status |
| --- | --- | --- | --- | --- |
| 1 | Partnership announcement — personalized message to all existing clients | Direct Phone + WhatsApp | Requires updated client contact list; include PDF catalog | To Do |
| 1 | Email blast: "Blau Batch is now a Coraplast Distributor" | Email | Requires email list; landing page or catalog link must be ready | To Do |
| 1 | LinkedIn post: Partnership announcement with Coraplast | LinkedIn | Include visual / banner; tag Coraplast if possible | To Do |
| 1 | Website: Add Coraplast section and partnership banner | Website | Must go live before or alongside email blast | To Do |
| 2 | Product spotlight: Black Masterbatch — introduction to grades and applications | LinkedIn + Email | Attach BLACK TDS samples; link to full catalog | To Do |
| 2 | Follow-up calls to clients who received Week 1 outreach | Direct Phone | Track responses; qualify leads for sample request | To Do |
| 3 | Technical post: "Choosing the right Black Masterbatch grade for your process" | LinkedIn | Educational — positions Blau Batch as a technical expert | To Do |
| 3 | Email: Black Masterbatch product guide with key grades (PE and PP) | Email | Include prices or CTA to request a quote | To Do |
| 4 | Product spotlight: White Masterbatch — TiO2 grades and food compliance | LinkedIn + Email | Highlight EU AP 89/1 and FDA compliance; target packaging buyers | To Do |
| 4 | Direct outreach to new prospects: packaging companies and plastic manufacturers | Phone + Email | Use prospect list from industry contacts and LinkedIn search | To Do |
| 5 | Technical post: "White Masterbatch: TiO2 content vs. opacity — what you need to know" | LinkedIn | Educational content; drives engagement from packaging engineers | To Do |
| 5 | Email: Specialty Additives from Coraplast (UV stabilizers, Processing Aids, Slip agents) | Email | Broadens the product offering; targets technically sophisticated buyers | To Do |
| 6 | Case use post: "Black Masterbatch for pipe and conduit applications" | LinkedIn | Targets construction sector; reference UV and HAF grades | To Do |
| 6 | Mid-campaign lead review and follow-up to all inquiries received | Phone + WhatsApp | Qualify leads; push sample/trial requests to close | To Do |
| 7 | Colored Masterbatch on request — awareness post and email | LinkedIn + Email | Highlight custom color capability; invite inquiries | To Do |
| 7 | Client testimonial / early adopter social proof post (if available) | LinkedIn | Requires at least one client to have trialed product by this point | To Do |
| 8 | Campaign close: "Limited time trial offer" email to qualified leads | Email + WhatsApp | Final push to convert warm leads; include direct call-to-action | To Do |
| 8 | Campaign performance report and pipeline review | Internal | Compare results to KPIs; plan next phase | To Do |

# 6. Content Assets Needed

| Asset | Description | Type | Priority | Due By |
| --- | --- | --- | --- | --- |
| Coraplast Product Catalog (Blau Batch branded) | PDF listing all Black and White grades with key specs and application guide | PDF | Must-Have | Week 1 |
| Partnership Announcement Email | HTML email to existing client list announcing the Coraplast distribution | Email | Must-Have | Week 1 |
| LinkedIn Partnership Post | Announcement post with visual; professional tone; links to website | Social Post | Must-Have | Week 1 |
| Website Coraplast Page | New page on blaubatch.com listing Coraplast products with inquiry form | Web Page | Must-Have | Week 1 |
| WhatsApp Broadcast Message | Short, professional announcement for broadcast to client contacts | Message Copy | Must-Have | Week 1 |
| Black Masterbatch Product Email | Dedicated email on Black grades with grade selection guide | Email | Must-Have | Week 3 |
| White Masterbatch Product Email | Dedicated email on White grades with compliance highlights | Email | Must-Have | Week 4 |
| 3x LinkedIn Technical Posts | Educational posts: grade selection, food compliance, and construction uses | Social Posts | Must-Have | Weeks 3–6 |
| Partnership Visual / Banner | Co-branded Blau Batch + Coraplast banner for social and email header | Design | Must-Have | Week 1 |
| Sample / Trial Request Form | Simple web or PDF form for prospects to request a product sample | Form | Nice-to-Have | Week 2 |
| Additives Spotlight Email | Email highlighting UV stabilizers, processing aids, and slip agents | Email | Nice-to-Have | Week 5 |

# 7. Success Metrics (KPIs)

| Metric | Target | How to Track | Reporting Cadence |
| --- | --- | --- | --- |
| Qualified leads generated | 60+ leads | CRM / manual log of inquiries | Weekly |
| Product trial / sample requests | 15+ requests | Form submissions + direct requests | Weekly |
| Existing clients reached (Week 1) | 100% of active clients | Call log + WhatsApp delivery | End of Week 1 |
| Email open rate | >30% | Email platform analytics | Per campaign send |
| LinkedIn post engagement rate | >3% per post | LinkedIn page analytics | Weekly |
| New clients converted (first purchase) | 5+ new clients | Sales records | End of campaign (Week 8) |
| Website page visits (Coraplast page) | 300+ visits | Google Analytics or website stats | Weekly |

# 8. Risks & Mitigations

| # | Risk | Likelihood | Mitigation |
| --- | --- | --- | --- |
| 1 | Low market awareness of Coraplast brand in Egypt | Medium | Lead with Blau Batch's trusted brand; position Coraplast's technical credentials and compliance specs as proof of quality |
| 2 | Slow uptake from existing clients — preference for current suppliers | Medium | Offer free samples or trial quantities in first 30 days; reduce switching cost perception through side-by-side spec comparison |
| 3 | Content production delays pushing campaign launch back | Low-Medium | Prioritize catalog and announcement email — these are the only Week 1 blockers. Other assets can follow in subsequent weeks. |
| 4 | Price sensitivity — Egyptian market may resist EGP pricing vs local alternatives | Medium | Emphasize total value: quality consistency, food compliance, technical support. Use spec comparison to justify premium. Offer volume pricing discussion. |

# 9. Immediate Next Steps

| # | Action | Owner | Deadline |
| --- | --- | --- | --- |
| 1 | Compile complete active client contact list (phone + email + WhatsApp) | Blau Batch Sales | Before Week 1 |
| 2 | Create co-branded Coraplast product catalog PDF (Blau Batch distribution version) | Marketing | Before Week 1 |
| 3 | Design partnership visual / banner for social and email | Marketing / Design | Before Week 1 |
| 4 | Draft and test announcement email — send to full client list on Day 1 | Marketing | Week 1, Day 1 |
| 5 | Add Coraplast product section to blaubatch.com website | Web / Marketing | Week 1 |
| 6 | Begin direct phone calls to all existing clients to introduce the partnership | Sales | Week 1–2 |
| 7 | Set up lead tracking log (spreadsheet or CRM) to track all inquiries and follow-ups | Sales / Marketing | Before Week 1 |
| 8 | Post partnership announcement on LinkedIn with co-branded visual | Marketing | Week 1, Day 1 |

BLAU BATCH  |  www.blaubatch.com

Official Distributor for Coraplast Masterbatch